## JACKWELL Comp stat (hidden)
Comparative Statement for C/o of Jack well Kamalapur
Sl.No. | Description of item | As per Sanction Estimate |  |  |  | As per Working Estimate |  |  |  | Excess | Less | Remarks
|  | Qty | Rate | Per | Amount | Qty | Rate | Per | Amount
1 | Earth Work Excavation for Intake well in all soils (excluding HR requiring blasting) under water including all leads ,lifts ,bailing out water
| 0 to 2m deep under water OG soils | 993.56 | 42.38 | cum | 42102 | 380.0306 | 132.3 | cum | 50278 | 8176 |  | As per revised designs and due to change in the location of jack well in Pedda cheruvu of Tadikal village
| 2 to 3m deep under water HG soils | 496.78 | 47.69 | cum | 23690 | 221.6943 | 170.1 | cum | 37710 | 14020
| 3 to 4m deep under water mixture of gravel | 220.35 | 50.74 | cum | 11180 | [5 empty] | 11180
| 4to 5m deep under water SDR soils | 220.35 | 61.13 | cum | 13471 | [5 empty] | 13471
| 5to 6m deep under water stone matrix | 220.35 | 65.88 | cum | 14517 | [5 empty] | 14517
| 6to 7m deep under water stone matrix | 54.76 | 148.93 | cum | 8155 | [5 empty] | 8155
| 7to 8m deep under water HDR soils without blasting | 54.76 | 179.67 | cum | 9838 | [5 empty] | 9838
| 8 to 9m deep under water HDR soils without blasting | 43.81 | 186.45 | cum | 8168 | [5 empty] | 8168
| 3 to 4m deep under water in SDRsoils |  |  |  |  | 232.6931 | 226.9 | cum | 52798 | 52798
| 4to 5m deep under water SDR soils |  |  |  |  | #REF! | #REF! | cum | #REF! | #REF! | #REF!
| 5to 6m deep under water SDR soils |  |  |  |  | #REF! | #REF! | cum | #REF! | #REF! | #REF!
| 6to 7m deep under water in HDR soils |  |  |  |  | #REF! | #REF! | cum | #REF! | #REF! | #REF!
| 7to 8m deep under water HDR soils |  |  |  |  | #REF! | #REF! | cum | #REF! | #REF! | #REF!
| 8 to 8.20m deep under water HDR soils |  |  |  |  | #REF! | #REF! | cum | #REF! | #REF! | #REF!
2 | CC (1:3:6) using 40 mm 70% +20mm of 30% HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for foundation levelling course
| For Base course under water | 16.43 | 2909.33 | cum | 47794 | 9.3517 | 4781.6 | cum | 44716 |  | 3078
3 | VCC (1:2:4) using 20mm HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for gap portion levelling under water |  |  |  |  | 9.3517 | 8756.2 | cum | 81886 | 81886
4 | VRCC (1:1.5:3) using 20 mm HBG crushed metal including cost and conveyence of all materials and labour charges but excluding cost of steel and its fabrication charges etc., complete as per standard specifications for Jack well
a | for Bottom Raft slab under water | 23.59 | 6462.45 | cum | 152427 | 8.3127 | 12589.3576 | cum | 104651 |  | 47776
b | for Bottom Raft beam under water | 5.34 | 5720.95 | cum | 30572 | 1.2158 | 11736.4 | cum | 14269 |  | 16303
c | for Side wall from 8.00 to 6m below GL | 9.2 | 8924.75 | cum | 82137 | 0 | 0 | cum | 0 |  | 82137
| for Side wall from 4m to 6.00m below GL under water | 11.88 | 8783.05 | cum | 104301 | 4.0527 | 17407.4549 | cum | 70546 |  | 33755
| for Side wall from 0.00m to 4.00m below GL under water | 23.75 | 8761.35 | cum | 208086 | 12.158 | 13339.129 | cum | 162177 |  | 45909
d | for Side wall above GL
| for Side wall upto 5m above GL | 29.69 | 8761.35 | cum | 260107 | 12.158 | 13339.129 | cum | 162177 |  | 97930
| for Side wall 5- 8m above GL | 11.88 | 8842.3 | cum | 105004 | [5 empty] | 105004
e | for Side wall above Foot Bridge (pump room)
| for Side wall upto 5m above GL |  |  |  |  | 2.097 | 19424.9165 | cum | 40734.3042 | 40734.3042
| for side wall 6.36 -8m above GL | 3.04 | 12802.15 | cum | 38912 | 7.4701 | 19729.4047 | cum | 147379.6864 | 108467.6864
| for Side wall 8- 11m above GL | 6.24 | 12874.05 | cum | 80314 | [5 empty] | 80314
| for Side wall 11.0- 14.0m above GL | 3.04 | 12945.95 | cum | 39349 | [5 empty] | 39349
f | for Bottom slab of pump room | 10.69 | 10036.14 | cum | 107277 | 4.0842 | 17538.3 | cum | 71629 |  | 35648
g | for L Beams of bot. slab for pump room | 2.88 | 8354.18 | cum | 24060 | 1.2987 | 14324.5 | cum | 18603 |  | 5457
h | for Top slab of pump room | 8.71 | 10198.64 | cum | 88863 | 3.9631 | 15542.1 | cum | 61595 |  | 27268
| for I Beams of top slab for pump room |  |  |  |  | 1.6902 | 14324.5 | cum | 24211 | 24211
i | for vertical wall around the projection slab | 2.67 | 16942.9 | cum | 45244 | 1.7907 | 19729.4047 | cum | 35330 |  | 9914
4 | Water Proof cement paint of superior quality, plastering with CM(1:3) prop. 12 mm thick with including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for | 934.81 | 107.45 | Sqm | 100442 | 450.0017 | 1451.3 | Sqm | 65309 |  | 35133
5 | Snowcem painting with 2 coats over a primary coat including cost and conveyance of all materials and labour charges etc., complete as per standard specifications | 934.81 | 53.1 | Sqm | 49642 | 450.0017 | 1027 | Sqm | 46215 |  | 3427
6 | Provision for Supply and fixing of MS Rolling Shutter including cost and conveyance of all materials and labour charges etc., complete as per standard specifications | 12 | 2000 | Sqm | 24000 | 2.52 | LS | Sqm | 10000 |  | 14000
7 | Provision for Supply and fixing of MS windows of 1.0 x 1.2 m size including cost and conveyance of all materials and labour charges etc., complete as per standard specifications | 3.24 | Ls | Sqm | 15000 | 3.24 | Ls | Sqm | 12000 |  | 3000
8 | Provision for Supply and fixing of MS ventilaters of 0.9 x 0.6 m size including cost and conveyance of all materials and labour charges etc., complete as per standard specifications | 4.32 | Ls | Sqm | 3000 | [5 empty] | 3000
9 | Provision towards cost of steel and its fabrication charges for RCC items | 18.69 | 58988.9 | MT | 1019868 | 6 | 58988.9 | MT | 353933 |  | 665935
10 | Refilling with excavated earth/sand including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for back filling around well side walls. | 3935 | 15.82 | cum | 62252 | 0 | 15.82 | cum | 0 |  | 62252
11 | Provision for Supply and fixing of GI/MS pipe 0.25 m pieces of 250mm dia 4kg for relief water uplift, including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for side walls above GL | 48 | 200 | No | 9600 | 80 | Ls | No | 6500 |  | 3100
Wt/m
12 | ISLB 300X150mm Bottom slab | 1206.4 | 57770 | kg | 69694 | 395.85 | LS | Rmt | 20000 |  | 49694
13 | ISMB 450X150mm Top slab | 861.96 | 57770 | kg | 49795 | 333.04 | LS | Rmt | 25000 |  | 24795
14 | Add TP 25.98% | [7 empty] | #REF! | #REF! | #REF!
15 | Ls for U/S items such as Rock requiring blasting,price variations in materials etc., |  |  | LS | 51139 |  |  |  | 442846 | 391707
| Total estimated cost in rupees |  |  |  | 3000000 |  |  |  | #REF! | #REF! | #REF!
Excess/Less as per sanction and working estimate
|  |  | 3000000 | - | #REF! | = | #REF!
Difference as per Excess and Less
|  |  | #REF! | - | #REF! | = | #REF!

## JACKWELL 4m dia
| PROJECTION OF FOOTING FROM RAFT BEAM |  | 1 |  |  | side walls above GL= |  |  | 4 m
| DIA OF WELL |  | 4
| DEPTH OF WELL BELOW GL |  | 12 | 0.6 | 12.6
| PROJECTION OF pump room slab |  | 0.6
CPWS SCHEME TO
SUB ESTIMATE for C/O JACK WELL in
sl no | Item of work | Nos | L | B | D | Qty | Rate | Per | Amount
1 | Eearth Work Excavation for Intake well in all soils (Excluding HR reqiring blasting) under water including all leads ,lifts ,bailing out water
a | 0 to 3m deep under water, OG soils | p /4 | 12.7 | 12.7 | 3 | 380.0306 | 132.3 | cum | 50278
b | 3 to 6m deep under water, HG soils | p /4 | 9.7 | 9.7 | 3 | 221.6943 | 170.1 | cum | 37710
c | 6 to 12.6m deep under water,SDR soils | p /4 | 6.7 | 6.7 | 6.6 | 232.6931 | 226.9 | cum | 52798
2 | CC (1:3:6) using 40 mm HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for foundation levelling course under water
| For Base course | p /4 | 6.3 | 6.3 | 0.3 | 9.3517 | 4781.6 | cum | 44716
3 | VCC (1:1.5:3) using 20mm HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for gap portion levelling under water
| For Base course | p /4 | 6.3 | 6.3 | 0.3 | 9.3517 | 8756.2 | cum | 81886
4 | VRCC (1:1.5:3) using 20 mm HBG crushed metal including cost and conveyence of all materials and labour charges but excluding cost of steel and its fabrication charges etc., complete as per standard specifications for Jack well under water
a | for Bottom Raft slab | p X1 | 6.3 | 1.4 | 0.3 | 8.3127 | 12589.3576 | cum | 104651
b | for Bottom Raft beam | p X1 | 4.3 | 0.3 | 0.3 | 1.2158 | 11736.4 | cum | 14269
c | for Side wall below GL
| for Side wall from 12.00 to 11m below GL | p X1 | 4.3 | 0.3 | 0 | 0 |  | cum | 0
| for Side wall from 11.00 to 8m below GL | p X1 | 4.3 | 0.3 | 0 | 0 |  | cum | 0
| for Side wall from 8.0 to 6m below GL | p X1 | 4.3 | 0.3 | 0 | 0 |  | cum | 0
| for Side wall from 6.00 to 5m below GL | p X1 | 4.3 | 0.3 | 1 | 4.0527 | 17407.4549 | cum | 70546
| for Side wall from 5.00 to 4m below GL | p X1 | 4.3 | 0.3 | 1 | 4.0527 | 17255.2108 | cum | 69929
| for Side wall from 4.00 to 3m below GL | p X1 | 4.3 | 0.3 | 1 | 4.0527 | 17102.9667 | cum | 69312
| for Side wall upto 0 to 3m below GL | p X1 | 4.3 | 0.3 | 3 | 12.158 | 13339.129 | cum | 162177
d | for Side wall above GL upto Foot bridge
| for Side wall upto 0.00 to 3m above GL | p X1 | 4.3 | 0.3 | 3 | 12.158 | 13339.129 | cum | 162177 |  | 3.35
| for Side wall upto 3.00 to 4m above GL | p X1 | 12.3 | 0.3 | 1 | 11.5925 | 17102.9667 | cum | 198266 |  | 3.35
e | for Side wall above Foot Bridge (pump room)
| for Side wall 4- 5m above GL | p X1 | 4.45 | 0.15 | 1 | 2.097 | 19424.9165 | cum | 40734.3042
| for Side wall 5- 8m above GL | p X1 | 4.45 | 0.15 | 4 | 8.3881
| Deduct for door | 1 | 1.2 | 0.15 | 2.1 | -0.378
| window | 2 | 1.2 | 0.15 | 1.5 | -0.54
[6 empty] | 7.4701 | 19729.4047 | cum | 147379.6864
f | for Bottom slab of pump room | p X1 | 5.8 | 5.8 | 0.2 | 5.2842
| Deduct for opening at cental porton | 1X1 | 4 | 1.5 | 0.2 | -1.2
[5 empty] | Net qty | 4.0842 | 17538.3 | cum | 71629
g | for L Beams of bot. slab for pump room | 1 X2 | 4.81 | 0.3 | 0.45 | 1.2987 | 14324.5 | cum | 18603
h | for Top slab of pump room | p X1 | 5.8 | 5.8 | 0.15 | 3.9631 | 15542.1 | cum | 61595
i | for I Beams of top slab for pump room | 1 X2 | 6.26 | 0.3 | 0.45 | 1.6902 | 14324.5 | cum | 24211
j | for vertical wall around the projection slab | p X1 | 5.7 | 0.1 | 1 | 1.7907 | 19729.4047 | cum | 35330
60.291
5 | Impervios Coat plastering with CM(1:3) prop. 12 mm thick with including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for
| In side jack well | p X1 | 4 |  | 15.3 | 192.2655
| Out side jack well | p X1 | 4.6 |  | 8 | 115.6106
| slabs bot & top | p /4X4 | 5.8 | 5.8 |  | 105.6832
| for in & out side vertical wall on the projection | p X2 | 5.8 |  | 1 | 36.4425
[6 empty] | 450.0017 | 1451.3 | 10 sqm | 65309
6 | Snowcem painting with 2 coats over a primary coat including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
| In side pump room | p X1 | 4 |  | 5 | 192.2655
| Out side jack well | p X1 | 4.6 |  | 8 | 115.6106
| slabs bot & top | p /4X4 | 5.8 | 5.8 |  | 105.6832
| for in & out side vertical wall on the projection | p X2 | 5.8 |  | 1 | 36.4425
[6 empty] | 450.0017 | 1027 | 10 sqm | 46215
7 | Provision for Supply and fixing of MS door 1.20 x 2.10 m size including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
|  | 1X1 | 1.2 | 2.1 |  | 2.52 | LS |  | 10000
8 | Provision for Supply and fixing of MS windows of 0.90 x 1.2 m size including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
|  | 1X3 | 0.9 | 1.2 |  | 3.24 | Ls |  | 12000
9 | Provision towards cost of steel and its fabrication charges for RCC items |  |  |  |  | 6 | 58988.9 | MT | 353933
10 | Refilling with excavated earth/sand including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for back filling around well side walls.
|  | p X1 | 8.5 | 4.2 | 12.3 | 0 | 0 | cum | 0
11 | Provision for Supply and fixing of PVC pipe 0.45m pieces of 90mm dia for weapholes with wire mesh for strainers including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for side walls above GL
|  | 80 | Nos |  |  | 80 | Ls |  | 6500
12 | ISLB 300X150mm Bottom slab ( 37.70Kg/Rmt) | 1X5 | 2.1 |  |  | 395.85 | LS |  | 20000
13 | ISMB 450X150mm Top slab ( 72.4Kg/Rmt) | 1X1 | 4.6 |  |  | 333.04 | LS |  | 25000
14 | Ls for U/S items such as soil classification, Bailing of water etc., |  |  |  |  | LS |  |  | 442846
| Total estimated cost in rupees | [7 empty] | 2499999.9907 | 0.0093092
Superintending Engineer
RWS&S Circle Warangal
400000.0093
2028653.9907

## data
Data sheet for Jack well for CPWS Scheme to Medaram Jathara and Surrounding 8 Habitations in Warangal District
| Dia= | 6 | m |  | Depth below GL= | 8.2 |  | above GL= | 8.35
Sl no | Qty. |  | Description of item |  |  | Rate | per |  | Amount
[6 empty] | (Rs) | LILA 13% |  | (Rs)
| Skilled mason= |  |  |  |  | 258 | 33.54 | 291.54 | /day | 87.462
| Semi skilled mason= |  |  |  |  | 237 | 30.81 | 267.81 | /day | 187.467
| Man & Woman Mazdoor |  |  |  |  | 196 | 25.48 | 221.48 | /day | 274.929
Cement Mortar (1:3)
1 | 480 | Kgs | Cost of Cement |  |  | 4800 | 1 | Ton | 2304
| 1 | Cum | Cost of sand |  |  | 1169.4 | 1 | Cum | 1169.4
| 1 | Cum | Mixing charges |  |  | 28 | 1 | Cum | 28
|  |  | Add 13% | [5 empty] | 3.64
3505.04
2 |  | Cement Mortar (1:4)
| 360 | Kgs | Cost of Cement |  |  | 4800 | 1 | Ton | 1728
| 1 | Cum | Cost of sand |  |  | 1169.4 | 1 | Cum | 1169.4
| 1 | Cum | Mixing charges |  |  | 28 | 1 | Cum | 28
|  |  | Add 13% | [5 empty] | 3.64
2929.04
3 | Earth Work Excavation for Intake well in all soils (excluding HR requiring blasting) under water including all leads ,lifts including 4% TOT
| lifts charges | Total depth | 8.2 |  |  | initial rate | Dewatering |  | with TOT & LI
0 | 0 | 0 to 2m deep under water |  | in OG soils |  | 37.5 |  | Cum | 42.375
1 | 1.7 | 2 to 3m deep under water |  | in HG soils |  | 40.5 |  | Cum | 47.686
2 | 3.4 | 3 to 4m deep under water |  | in SDR soils |  | 49 | 80 | Cum | 139.212
3 | 5.1 | 4to 5m deep under water |  | in SDR soils |  | 49 | 80 | Cum | 141.133
4 | 7.8 | 5to 6m deep under water |  | in SDR soils |  | 49 | 80 | Cum | 144.184
5 | 17.7 | 6 to 7m deep under water |  | in HDR soils |  | 66 | 80 | Cum | 174.581
6 | 22.2 | 7to 8m deep under water |  | in HDR soils |  | 66 | 80 | Cum | 179.666
7 | 28.2 | 8 to 9m deep under water |  | in HDR soils |  | 66 | 80 | Cum | 186.446
4 | CC (1:3:6) using 40 mm 70%+20mm 30% HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for foundation levelling course under water inclueding c/c of
material, labour charges etc., complete
| 0.92 | Cum | Cost of 40mm HBG metal |  | 70% | 746 | 1 | Cum | 480.424
| 0.92 | Cum | Cost of 20mm HBG metal |  | 30% | 1298.825 | 1 | Cum | 358.4757
| 0.46 | Cum | Cost of CM (1:3) |  |  | 3505.04 | 1 | Cum | 1612.3184
| 0.2 | Nos. | Mason |  |  | 274.929 | 1 | Each | 54.9858
| 1.8 | Nos. | Men Mazdoor |  |  | 221.48 | 1 | Each | 398.664
| 1.4 | Nos. | Women Mazdoor |  |  | 221.48 | 1 | Each | 310.072
| 1 | Cum | Add Mixing Charges |  |  | 45 | 1 | Each | 45
|  |  | Add 13% | [5 empty] | 1.4625
|  |  | Sundries | [5 empty] | 0.01
[8 empty] | Rate for GL with initial lifts= | 3261.4124
| 1cum | Add for Bailing out water charges for CC laying in water as per sl no 357 of ssr = | [6 empty] | 120
[8 empty] | Rate for under water construction= | 3381.4124
| 1cum | Add for Delifting charges for CC laying for every 2m depth, over initial depth of 4m as per sl no 34 of ph ssr |  |  |  | 21.7 | 8.2 | 2 | 43.4
[8 empty] | for CC laying for 8.20m below GL under water = | 3424.8124
5 | VC (1:2:4) using 20mm HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for gap portion levelling under water including c/c of
material, labour charges etc., complete
| 0.92 | Cum | Cost of 20mm HBG metal |  |  | 1298.825 | 1 | Cum | 1194.919
| 0.46 | Cum | cost of sand |  |  | 1169.4 | 1 | Cum | 537.924
| 0.331 | MT | Cost of cement |  |  | 4800 | 1 | MT | 1588.8
| 0.2 | Nos. | Mason |  |  | 274.929 | 1 | Each | 54.9858
| 1.8 | Nos. | Men Mazdoor |  |  | 221.48 | 1 | Each | 398.664
| 1.4 | Nos. | Women Mazdoor |  |  | 221.48 | 1 | Each | 310.072
| 1 | Cum | Add Mixing Charges |  |  | 45 | 1 | Each | 45
| 1 | Cum | Vibrating charges |  |  | 43 | 1 | Each | 43
|  |  | Add 13% | [5 empty] | 2.86
|  |  | Sundries | [5 empty] | 0.02
[8 empty] | Rate for GL with initial lifts= | 4176.2448
| 1cum | Add for Bailing out water charges for CC laying in water as per sl no 357 of ssr = | [6 empty] | 120
[8 empty] | Rate for under water construction= | 4296.2448
| 1cum | Add for Delifting charges for CC laying for every 2m depth, over initial depth of 4m as per sl no 34 of ph ssr = |  |  |  | 21.7 | Cost of CM (1:3) | 2 | 43.4
[8 empty] | for CC laying for 8.20m below GL under water = | 4339.6448
6 | VRCC (1:1.5:3) using 20 mm HBG crushed metal including cost and conveyence of all materials and labour charges but excluding cost of steel and its fabrication charges etc., complete as per standard specifications for Jack well under water with water proof liquid
| 0.92 | Cum | Cost of 20mm HBG metal |  |  | 1298.825 | 1 | Cum | 1194.919
| 0.46 | Cum | Cost of sand |  |  | 1169.4 | 1 | Cum | 537.924
| 441.6 | Kgs | Cost of Cement |  |  | 4800 |  | Tonne | 2119.68
| 1.7664 | Ltrs | cocrete admixures & plasticisers |  |  | 70 | 1 | Ltr | 123.648
| 0.4 | No. | Mason |  |  | 274.929 |  | Each | 109.9716
| 2.1 | Nos. | Men Mazdoor |  |  | 221.48 |  | Each | 465.108
| 3.5 | Nos. | Women Mazdoor |  |  | 221.48 |  | Each | 775.18
| 1 | Cum | Add for vibrating charges |  |  | 43 | 1 | Cum | 43
| 1 | Cum | Add for Machine mixing concrete |  |  | 45 | 1 | Cum | 45
|  |  | Add 13% | [5 empty] | 2.86
[6 empty] | Rate on GL= |  |  | 5417.2906
6 | VRCC (1:1.5:3) using 20mm HBG metal including cost and conveyance
of all material, labour charges, centering etc., complete but
excluding cost of steel and its fabrication charges for
a | for Bottom Raft slab
|  | 0.3 | mm thick | under water
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
r&b | 1 | cum | Centering charges |  | lifts no | 715 | 1 | Cum | 715
|  |  | add 13% | [5 empty] | 23.2375
| 1 | Cum | Add Delifting | 7.9 | 2 | 21.7 | 1 | Cum | 43.4
|  |  | Add 13% | [5 empty] | 5.642
|  |  | Add for dewatering charges | [5 empty] | 120
6324.5701
b | for Bottom Raft beam |  |  | under water
|  | 0.3 | 0.3
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  | lifts no | 576.6 | 1 | sqm | 3844
|  |  | add 13% | [5 empty] | 124.93
| 1 | Cum | Add Delifting | 7.9 | 2 | 21.7 | 1 | Cum | 43.4
|  |  | Add 13% | [5 empty] | 5.642
|  |  | Add for dewatering charges | [5 empty] | 120
|  |  | Sundries | [5 empty] | 0.01
9555.2726
c | for Side wall above GL
|  | 0.3 | mm thick
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  |  | 576.6 | 1 | sqm | 3844
|  |  | Add 13% | [5 empty] | 124.93
9386.2206
|  |  | for Side wall above GL |  | 71.6
| Sl.No. | Unit | Item | Basic Rate | lifting charges | Add 13% |  | Total Rate | Per
| 1 | Cum | upto 4m above GL | 9386.2206 | 0 | 0 |  | 9386.25 | /1Cum
| 2 | Cum | 4- 6m above GL | 9386.2206 | 71.6 | 9.308 |  | 9467.15 | /1Cum
| 3 | Cum | 6- 8m above GL | 9467.1286 | 71.6 | 9.308 |  | 9548.05 | /1Cum
| 4 | Cum | 6- 8m above GL | 9548.0366 | 71.6 | 9.308 |  | 9628.95 | /1Cum
d | for Side wall below GL
|  | 0.3 | mm thick | under water
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  |  | 576.6 | 1 | sqm | 3844
|  |  | Add 13% | [5 empty] | 124.93
9386.2206
|  |  | for Side wall below GL |  | 21.7
| Sl.No. | Unit | Item | Basic Rate | De lifting charges | Add 13% | add dewatering charges | Total Rate | Per
| 1 | Cum | <4m below GL | 9386.2206 | 0 | 0 |  | 9386.2206 | /1Cum
| 2 | Cum | 4m to 6m below GL | 9386.2206 | 21.7 | 2.821 | 120 | 9530.7416 | /1Cum
| 3 | Cum | 6m to 8m below GL | 9410.7416 | 21.7 | 2.821 | 120 | 9555.2626 | /1Cum
| 4 | Cum | 8m-10m below GL | 9435.2626 | 21.7 | 2.821 | 120 | 9579.7836 | /1Cum
| 5 | Cum | 10m -12m below GL | 9459.7836 | 21.7 | 2.821 | 120 | 9604.3046 | /1Cum
| 6 | Cum | 12m -14m below GL | 9484.3046 | 21.7 | 2.821 | 120 | 9628.8256 | /1Cum
e | for Side wall of pumphouse
|  | 0.15 | mm thick
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 13.3333 | sqm | Centering charges |  | lifts no | 576.6 | 1 | sqm | 7688
|  |  | Add 13% | [5 empty] | 249.86
13355.1506
|  |  | for Side wall above GL |  | 71.6
| Sl.No. | Unit | Item | Basic Rate | lifting charges | Add 13% |  | Total Rate | Per
| 1 | Cum | 0- 5m above GL | 13355.1506 | 0 | 0 |  | 13355.1506 | /1Cum
| 2 | Cum | 5- 8m above GL | 13355.1506 | 71.6 | 9.308 |  | 13436.0586 | /1Cum
| 3 | Cum | 8- 11m above GL | 13436.0586 | 71.6 | 9.308 |  | 13516.9666 | /1Cum
| 4 | Cum | 11- 14m above GL | 13516.9666 | 71.6 | 9.308 |  | 13597.8746 | /1Cum
| 5 | Cum | 14- 17m above GL | 13597.8746 | 71.6 | 9.308 |  | 13678.7826 | /1Cum
f | for Bottom slab of pump room
|  | 0.2 | mm thick
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 5 | sqm | Centering charges |  | lifts no | 738.2 | 1 | sqm | 3691
|  |  | Add 13% | [5 empty] | 119.9575
| 1 | Cum | Add lifting | 4 m |  | 71.6 | 1 | Cum | 0
|  |  | Add 13% | [5 empty] | 0
|  |  | Sundries | [5 empty] | 0.01
9228.2581
g | for L Beams of bot. slab for pump room
|  | 0.3 | 0.45
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  | lifts no | 493.6 | 1 | sqm | 3290.6667
|  |  | Add 13% | [5 empty] | 106.9467
| 1 | Cum | Add lifting | 4 m |  | 71.6 | 1 | Cum | 0
|  |  | Add 13% | [5 empty] | 0
8814.9039
h | for Top slab of pump room
|  | 0.15 | mm thick
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  | lifts no | 738.2 | 1 | sqm | 4921.3333
|  |  | Add 13% | [5 empty] | 159.9433
| 1 | Cum | Add lifting | 8.35 | 2 | 71.6 | 1 | Cum | 143.2
|  |  | Add 13% | [5 empty] | 18.616
|  |  | Sundries | [5 empty] | 0.04
10660.4233
i | for T beams of Top slab for pump room
|  | 0.3 | 0.45
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 6.6667 | sqm | Centering charges |  | lifts no | 493.6 | 1 | sqm | 3290.6667
|  |  | Add 13% | [5 empty] | 106.9467
| 1 | Cum | Add lifting | 8.35 | 2 | 71.6 | 1 | Cum | 143.2
|  |  | Add 13% | [5 empty] | 18.616
8976.7199
j | for vertical wall around the projection slab
|  | 0.1 | mm thick
| 1 | Cum | Cost of VRCC (1:1.5:3) |  |  | 5417.2906 | 1 | Cum | 5417.2906
33 of ph | 20 | sqm | Centering charges |  | lifts no | 576.6 | 1 | sqm | 11532
|  |  | Add 13% | [5 empty] | 374.79
| 1 | Cum | Add lifting | 4 m |  | 71.6 | 1 | Cum | 0
|  |  | Add 13% | [5 empty] | 0
|  |  | Sundries | [5 empty] | 0.02
17324.1006
7 | Water Proof cement paint of superior quality ,plastering with CM (1:3) 12mm thick
including cost and conveyance of all material, labour charges etc., complete
| 0.15 | Cum | Cost of CM (1:3) |  |  | 3505.04 | 1 | Cum | 525.756
| 1.1 | Nos. | Mason charges |  |  | 274.929 |  | Each | 302.4219
| 0.5 | Nos. | Man Mazdoor |  |  | 221.48 |  | Each | 110.74
| 1.1 | Nos. | Women Mazdoor |  |  | 221.48 |  | Each | 243.628
bldg 251 | 2 | Ltr | Cost of Water Proof cement paint of superior quality |  |  | 35 | 1 | Ltr | 70
bldg 896 | 10 | sqm | Lifting charges |  |  | 11 |  | 1sqm | 11
|  |  | Add 13% | [5 empty] | 1.43
bldg 853 | 10 | sqm | Scaffolding charges |  |  | 40 |  | 10sqm | 40
|  |  | Add 13% | [5 empty] | 1.3
|  |  | Sundries | [5 empty] | 0.01
[8 empty] | 10 sqm | 1306.2859
[8 empty] | 1sqm | 130.6286
8 | Painting with Snowcem paint 2 coats over a primary coat including cost
and conveyance of all materials and labour charges, etc., complete
| 3.5 | Kg | Snowcem paint |  |  | 38 | 1 | KG | 133
| 0.5 | Nos. | Painters |  |  | 274.929 |  | Each | 137.4645
| 0.5 | Nos. | Man mazdoor |  |  | 221.48 |  | Each | 110.74
| 1 | Nos. | Woman mazdoor |  |  | 221.48 |  | Each | 221.48
bldg 853 | 10 | sqm | Scaffolding charges |  |  | 40 |  | 1sqm | 40
|  |  | Add 13% | [5 empty] | 1.3
[8 empty] | 10 sqm | 643.9845
[8 empty] | 1sqm | 64.3984
9 | Cost and supply of steel including transportation, TOT etc., complete
|  | MT | Cost of steel |  |  | 39000 | 1 | MT | 39000
| 1 | MT | Fabrication charges |  |  | 9000 | 1 | MT | 9000
|  |  | Add 13% | [5 empty] | 1053
Sundries
[7 empty] | 1 | MT | 49053
10 | Cost and supply of steel including transportation, TOT etc., complete
|  | MT | Cost of steel |  |  | 39000 | 1 | MT | 39000
| 1 | MT | Fabrication charges |  |  | 9000 | 1 | MT | 9000
|  |  | Add 13% | [5 empty] | 1053
Sundries
[7 empty] | 1 | MT | 49053
Asst.Executiven Engineer |  |  | Dy.Executive Engineer |  | Executive Engineer |  |  | Superintending Engineer
RWS&S Tadvai |  |  | RWS&S Mulugu (P) |  | RWS&s Div Warangal |  |  | RWS&S Circle Warangal

## lead
Leads statement
CPWSS to Kamalapur and other habitations in Kamalapur mandal in Karimnagar District
Name of the work : Construction of Jack well with 6.0m dia
Sl.No | Description of material | Name of the Quarry | lead (km) | Initial cost | Conveyance | Stacking | Blasting charges | Machine crushing | seignorage | Total
1 | 40mm size HBG (SS5) | Baopet | 15 | 500 | 143.4 | 17.4 | 70 |  | 50 | 746
2 | 20mm size HBG metal | Baopet | 15 | 844 | 143.4 | 17.4 | 70 | 208.825 | 50 | 1298.825
3 | CR Stone | Baopet | 15 | 321 | 143.4 | 17.4 | 69 |  | 50 | 566
4 | RR Stone | Baopet | 15 | 205 | 143.4 | 17.4 | 67 |  | 50 | 448
5 | Sand for mortar | Chegyam | 120 | 220 | 920.4 | 11 |  |  | 40 | 1169.4
6 | Sand for filling | Shanigaram | 10 | 70 | 100.4 | 11 |  |  | 40 | 199.4
7 | Bricks | Huzurabad | 15 | 3100 | 476.49 | 10 |  |  | 36 | 3602.49
8 | Cement |  |  | 4800 | [5 empty] | 4800
9 | Steel |  |  | 39000 | [5 empty] | 39000
Certified that the leads adopted above are average and quarry is blasting variety to the best of my knowledge
Sl. | Name of | Quarry | Lead in | Lead | Initial | Seigniorage | Blasting | Machine crushing | Deduct | Net
No. | the material |  | Km. | cost | cost | charges | charges |  | stacking | Amount
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
1 | Sand for filling | Shanigaram | 10 | 100.4 | 70 | 40 |  |  | 11 | 221.4
2 | Sand for mortar | Chegyam | 120 | 920.4 | 220 | 40 |  |  | 11 | 1191.4
3 | 40mm HBG metal | Baopet | 15 | 143.4 | 500 | 50 | 70 | 125 | 17.4 | 905.8
4 | 20mm HBG metal | Baopet | 15 | 143.4 | 844 | 50 | 70 | 211 | 17.4 | 1335.8
5 | Cement |  |  |  | 4800 |  |  |  |  | 4800
6 | Steel |  |  |  | 39000 |  |  |  |  | 39000
7 | 12 mm HBG metal | Baopet | 15 | 143.4 | 688 | 50 | 70 | 172 | 17.4 | 1140.8
8 | 6 mm HBG metal | Baopet | 15 | 143.4 | 428 | 50 | 70 | 107 | 17.4 | 815.8

## Scour-chamber-in Lake (hidden)
| PROJECTION OF FOOTING FROM RAFT BEAM |  | 0.6 |  |  | side walls above GL= |  |  | 8
| DIA OF WELL |  | 4
| DEPTH OF WELL BELOW GL |  | 13 | 0.9 | 13.9
| PROJECTION OF pump room slab |  | 0.6
CPWS Scheme MULUGU under PHASE-1
SUB ESTIMATE for C/O Scour Chamber with sluice Valve Arrangemets at scour chamber in Ramappa Lake (under water)
sl no | Item of work | Nos | L | B | D | Qty | unit | Rate | Amount
1 | Eearth Work Excavation for Intake well in all soils (excluding HR requiring blasting) under water including all leads ,lifts ,shoring,strutting ,bailing out water and removal of shoring & strutting meterials after completion of work as per PH ssr item no | [8 empty] | 11.9
a | 0 to 1m deep under water | p /4 | 5.85 | 5.85 | 1 | 26.8783 | cum | 37.5 | 1007.9358
b | 1 to 2m deep under water | p /4 | 5.85 | 5.85 | 1 | 26.8783 | cum | 40.5 | 1088.5707
c | 2 to 5m deep under water | p /4 | 5.85 | 5.85 | 3 | 80.6349 | cum | 49 | 3951.1084
d | 5 to 14.5m deep under water | p /4 | 5.85 | 5.85 | 8.9 | 239.2168 | cum | 49 | 11721.6217
2 | CC (1:3:6) using 40 mm 70% +20mm of 30% HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for foundation levelling course under water
| For Base course | p /4 | 5.85 | 5.85 | 0.3 | 8.0635 | cum | 3424.8124 | 27615.9289
3 | VRCC (1:1.5:3) using 20 mm HBG crushed metal including cost and conveyence of all materials and labour charges but excluding cost of steel and its fabrication charges etc., complete as per standard specifications for scour chamber under water
a | for Bottom Raft slab | p /4 | 5.85 | 5.85 | 0.45 | 12.0952 | cum | 6324.5701 | 76497.1293
b | for Bottom Raft beam | p X1 | 4.2 | 0.45 | 0.6 | 3.5626 | cum | 9555.2726 | 34041.2899
c | for Side wall below GL
| for Side wall upto 4m below GL | p X1 | 4.2 | 0.2 | 4 | 10.5558 | cum | #REF! | #REF!
| for Side wall 4m to 6m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 6m to 8m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 8m to 10m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 10m to 12m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 12m to 14m below GL | p X1 | 4.2 | 0.2 | 1.15 | 3.0348 | cum | #REF! | #REF!
d | for Side wall above GL
| for Side wall upto 5m above GL | p X1 | 4.2 | 0.2 | 5 | 13.1947 | cum | 9386.25 | 123848.651
| for Side wall 5- 8m above GL | p X1 | 4.2 | 0.2 | 3 | 7.9168 | cum | 9467.15 | 74949.6608
f | for slab of over chamber | p /4 | 5.6 | 5.6 | 0.15 | 3.6945 | cum
| Deduct for opening manholes | 1X5 | 0.6 | 0.6 | 0.15 | -0.27 | cum
[5 empty] | Net qty | 3.4245 | cum | 9228.2581 | 31602.2895
g | for Beams of slab of over chamber | 1 X2 | 5.6 | 0.23 | 0.23 | 0.59248 | cum | 8814.9039 | 5222.6543
4 | Water Proof cement paint of superior quality, plastering with CM(1:3) prop. 12 mm thick with including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for
| side walls In side scour chamber | p X1 | 4 |  | 21.75 | 273.3186 | sqm
| side walls Out side scour chamber | p X1 | 4.4 |  | 21.75 | 300.6504 | sqm
| slabs bot & top | p /4 X2 | 4 | 4 |  | 25.1327 | sqm
| for in & out side slab projection | p X2 | 4.6 |  | 1.2 | 34.6832 | sqm
[6 empty] | 633.7849 | sqm | 130.6286 | 82790.4281
5 | Snowcem painting with 2 coats over a primary coat including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
| side walls Out side scour chamber | p X1 | 4.4 |  | 8 | 300.6504 | sqm
| for in & out side slab projection | p X2 | 4.6 |  | 1.2 | 34.6832 | sqm
[6 empty] | 335.3336 | sqm | 64.3984 | 21594.9641
6 | Provision for Supply and fixing of Scour Valve of 300mm dia size including cost and conveyance of all materials including long rod upto top of chamber etc.,arrangements for sluice operation and labour charges etc., complete as per standard specifications
|  | 1 | No |  |  | 1 | sqm | 63713 | 63713
7 | Provision towards cost of steel and its fabrication charges for RCC items |  |  |  |  | 8.3037 | MT | 49053 | 407322.1633
8 | Refilling with excavated earth/sand including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for back filling around well side walls.
|  | p X1 | 5.025 | 0.825 | 13.6 | 177.1246 | cum | 7 | 1239.872
9 | Manhole cover Arrangements HD 35 with 560 mm Dia Clear opening on TOP of chamber including TOT sas per BIS 12592 (Part I &II)
|  | 5 | Nos |  |  | 5 | No | 915.2 | 4576
10 | provision for CED and other taxes if applicable | [7 empty] | 20000
11 | Ls for U/S items such as Rock requiring blasting,price variations materials etc., | [6 empty] | LS | 131262
| Total estimated cost in rupees | [7 empty] | #REF!
#REF!

## Inlet-chamber-in Lake (hidden)
| PROJECTION OF FOOTING FROM RAFT BEAM |  | 0.6 |  |  | side walls above GL= |  |  | 8
| DIA OF WELL |  | 4
| DEPTH OF WELL BELOW GL |  | 11 | 0.9 | 11.9
| PROJECTION OF pump room slab |  | 0.6
CPWS Scheme MULUGU under PHASE-1
SUB ESTIMATE for C/O Inlet Chamber with sluice Gates Arrangemets at Inlet chamber in Ramappa Lake (under water)
sl no | Item of work | Nos | L | B | D | Qty | unit | Rate | Amount
1 | Eearth Work Excavation for Intake well in all soils (excluding HR requiring blasting) under water including all leads ,lifts ,shoring,strutting ,bailing out water and removal of shoring & strutting meterials after completion of work as per PH ssr item no | [8 empty] | 11.9
a | 0 to 1m deep under water | p /4 | 5.85 | 5.85 | 1 | 26.8783 | cum | 37.5 | 1007.9358
b | 1 to 2m deep under water | p /4 | 5.85 | 5.85 | 1 | 26.8783 | cum | 40.5 | 1088.5707
c | 2 to 5m deep under water | p /4 | 5.85 | 5.85 | 3 | 80.6349 | cum | 49 | 3951.1084
d | 5 to 14.5m deep under water | p /4 | 5.85 | 5.85 | 6.9 | 185.4602 | cum | 49 | 9087.5494
2 | CC (1:3:6) using 40 mm 70% +20mm of 30% HBG metal including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for foundation levelling course under water
| For Base course | p /4 | 5.85 | 5.85 | 0.3 | 8.0635 | cum | 3424.8124 | 27615.9289
3 | VRCC (1:1.5:3) using 20 mm HBG crushed metal including cost and conveyence of all materials and labour charges but excluding cost of steel and its fabrication charges etc., complete as per standard specifications for Inlet chamber under water
a | for Bottom Raft slab | p /4 | 5.85 | 5.85 | 0.3 | 8.0635 | cum | 6324.5701 | 50998.0862
b | for Bottom Raft beam | p X1 | 4.2 | 0.45 | 0.6 | 3.5626 | cum | 9555.2726 | 34041.2899
c | for Side wall below GL
| for Side wall upto 4m below GL | p X1 | 4.2 | 0.2 | 4 | 10.5558 | cum | #REF! | #REF!
| for Side wall 4m to 6m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 6m to 8m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 8m to 10m below GL | p X1 | 4.2 | 0.2 | 2 | 5.2779 | cum | #REF! | #REF!
| for Side wall 10m to 12m below GL | p X1 | 4.2 | 0.2 | 1 | 2.6389 | cum | #REF! | #REF!
d | for Side wall above GL
| for Side wall upto 5m above GL | p X1 | 4.2 | 0.2 | 5 | 13.1947 | cum | 9386.25 | 123848.651
| for Side wall 5- 8m above GL | p X1 | 4.2 | 0.2 | 3 | 7.9168 | cum | 9467.15 | 74949.6608
f | for slab of over chamber | p /4 | 5.6 | 5.6 | 0.15 | 3.6945 | cum
| Deduct for opening manholes | 1X5 | 0.6 | 0.6 | 0.15 | -0.27 | cum
[5 empty] | Net qty | 3.4245 | cum | 9228.2581 | 31602.2895
g | for Beams of slab of over chamber | 1 X2 | 5.6 | 0.23 | 0.23 | 0.59248 | cum | 8814.9039 | 5222.6543
4 | Water Proof cement paint of superior quality, plastering with CM(1:3) prop. 12 mm thick with including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for
| side walls In side Inlet chamber | p X1 | 4 |  | 19.6 | 246.3009 | sqm
| side walls Out side Inlet chamber | p X1 | 4.4 |  | 19.6 | 270.931 | sqm
| slabs bot & top | p /4 X2 | 4 | 4 |  | 25.1327 | sqm
| for in & out side slab projection | p X2 | 4.6 |  | 1.2 | 34.6832 | sqm
[6 empty] | 577.0477 | sqm | 130.6286 | 75378.9325
5 | Snowcem painting with 2 coats over a primary coat including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
| side walls Out side Inlet chamber | p X1 | 4.4 |  | 8 | 270.931 | sqm
| for in & out side slab projection | p X2 | 4.6 |  | 1.2 | 34.6832 | sqm
[6 empty] | 305.6141 | sqm | 64.3984 | 19681.0765
6 | Provision for Supply and fixing of Inlet Sluice Gate of 1200X 1200 mm size including cost and conveyance of all materials and labour charges etc., complete as per standard specifications
|  | 1 | No |  |  | 1 | sqm | 150000 | 150000
7 | Provision for Supply and fixing of Inlet sluice Valve of 400mm dia size including cost and conveyance of all materials including long rod upto top of chamber etc.,arrangements for sluice operation and labour charges etc., complete as per standard specifications
|  | 3 | No |  |  | 3 | sqm | 120967 | 362901
8 | Provision towards cost of steel and its fabrication charges for RCC items |  |  |  |  | 7.2361 | MT | 49053 | 354953.1531
9 | Refilling with excavated earth/sand including cost and conveyance of all materials and labour charges etc., complete as per standard specifications for back filling around well side walls.
|  | p X1 | 5.025 | 0.825 | 11.6 | 151.0768 | cum | 7 | 1057.5378
10 | Manhole cover Arrangements HD 35 with 560 mm Dia Clear opening on TOP of chamber including TOT sas per BIS 12592 (Part I &II)
|  | 5 | Nos |  |  | 5 | No | 915.2 | 4576
11 | provision for CED and other taxes if applicable | [7 empty] | 20000
12 | Ls for U/S items such as Rock requiring blasting,price variations materials etc., | [6 empty] | LS | 82807
| Total estimated cost in rupees | [7 empty] | #REF!
#REF!